## Introduction
Online Airline Reservation and Flight Management System
What is this? | This workbook is meant to help manage and piroritize the user stories and features using scrum.
How to use and read this document? | Before project start: The product owner is responsible for managing and maintaining the product backlog of user stories.
Before each sprint: The vendor will break down the user stories into tasks.
Notes | Cells that you can edit have a blue background.
Sprints are assumed to be 2 weeks long (10 working days)/
Licence | This work is licensed under a Creative Commons Attribution-Share Alike 3.0 Unported License.
Origins | This work is inspired by the Scrum Template published by Nicolas Martignole on his "Touilleur Express" blog. Adapted by Olivier Gérardin.

## Product backlog
Project Name
| Organizations | Colorado Technical University, Group 8
| Project | Online Airline Reservation and Flight Management System
| Product Owner | Kendal Runnels
| Scrum Master | Sawyer Smith
| Development Team | Preston Schave (Lead Developer / System Architect); Cheyne Sersen (Frontend Developer / QA Tester)
Story ID | Title | Description | Acceptance Criteria | Priority # | Sprint # | Responsibility
E-01 | Secure Customer and Agent Access | As a customer or airline agent, I want to create an account and sign in with a role-appropriate profile so that only authorized users can search protected records, book travel, or manage airline operations. | 1. A new customer can register with a unique email address and a password that meets the project's password rules. 2. Customers and agents sign in through separate or clearly distinguished roles, and each role receives only the screens and data required for that role. 3. Passwords are stored as salted hashes; the full password is never saved or displayed. 4. Failed sign-in attempts return a generic error and do not confirm whether an email address is registered. 5. After logout or session timeout, protected pages and APIs reject the prior session and require a new sign-in. 6. An unauthenticated user cannot view another person's reservation, payment, or agent-sales information. | 1 | 1 | Preston Schave
E-02 | Flight Search and Availability | As a customer, I want to search for available flights by origin, destination, and travel date so that I can compare options and choose a flight that meets my travel needs. | 1. The customer can submit a search using origin, destination, and travel date. 2. Matching flights display destination, departure and arrival information, and whether seats remain available. 3. When no flights match the search, the system displays a clear no-results message. 4. Search results do not expose another customer's name, reservation, or payment data. 5. Invalid or incomplete search input is rejected with a helpful validation message. | 2 | 1 | Cheyne Sersen
E-03 | Create Flight Reservation | As a customer, I want to select a flight and create a reservation so that my booking is recorded against that flight and I can continue to payment. | 1. An authenticated customer can select a flight from search results and enter required passenger details. 2. The system creates a reservation record linked to the selected flight and destination and issues a reservation identifier. 3. If the flight is no longer available, the reservation is rejected and the customer is told to choose another flight. 4. The customer can later retrieve the same reservation using the identifier while signed in. 5. A customer cannot create or overwrite a reservation that belongs to another customer. | 3 | 1 | Preston Schave
E-04 | Secure Credit Card Payment and Ticket Sale | As a customer, I want to pay for a reservation with a credit card so that I can complete the ticket purchase online without visiting an agent. | 1. Payment is accepted only for an existing unpaid reservation owned by the signed-in customer. 2. Card data is submitted over HTTPS; the full card number is not stored in the application database. 3. A successful payment creates a ticket-sale record linked to the reservation, flight, and destination. 4. A declined or failed payment does not issue a ticket, and the customer sees a clear failure message. 5. Payment attempts are written to an audit log using a masked card number only (for example, last four digits). 6. Tampered or replayed payment requests are rejected. | 4 | 2 | Preston Schave
E-05 | Review and Manage Reservations | As a customer, I want to review my reservation and ticket information so that I can confirm flight details, payment status, and booking identity after I purchase travel. | 1. A signed-in customer can open a list of that customer's reservations only. 2. Each reservation view shows flight, destination, passenger information, ticket or payment status, and the reservation identifier. 3. Requesting another customer's reservation identifier returns an access-denied or not-found result, not the other booking. 4. Canceled or unpaid reservations are labeled so the customer can distinguish them from confirmed tickets. | 5 | 2 | Cheyne Sersen
E-06 | Flight Status Lookup | As a customer, I want to check the current status of a flight so that I know whether my travel is on time, delayed, or canceled. | 1. A customer can look up status by flight number or by a reservation the customer owns. 2. The displayed status matches the airline record (on time, delayed, or canceled) and includes destination and scheduled times. 3. The status view does not list other passengers or their contact information. 4. An unknown flight number returns a not-found message rather than an error page. | 6 | 2 | Cheyne Sersen
E-07 | Airline Flight and Reservation Operations | As airline personnel, I want to view and update flight and reservation records so that the airline can keep schedules, bookings, and ticket-sale information accurate. | 1. An authenticated agent can view flights, destinations, reservations, and ticket-sale records needed for operations. 2. An authorized agent can update flight time or status, and the change appears on later customer status and reservation views. 3. Customers cannot open agent operations screens or application programming interfaces. 4. Each operational change records the agent, timestamp, and previous value in an audit entry. 5. Agents cannot delete audit history or payment logs. | 7 | 2 | Preston Schave
E-08 | Agent Sales Tracking and Reporting | As an airline supervisor or agent, I want ticket sales attributed to the agent who completed them so that the airline can review sales activity and agent performance. | 1. Each agent-assisted ticket sale stores the agent identifier along with the reservation and flight. 2. An authorized user can view a sales summary grouped by agent for a selected date range. 3. An agent cannot change or reassign another agent's completed sales records. 4. Sales reports never include full credit-card numbers; only masked payment references are shown. 5. Customer self-service purchases are labeled as online sales rather than as an agent's personal sales. | 8 | 3 | Preston Schave
E-09 | Flight Cancellation and Customer Notification | As airline operations staff, I want to cancel or modify a flight and notify every affected customer so that travelers can respond quickly without relying on a paper or agent-only process. | 1. An authorized agent can mark a flight as canceled or modified and save the reason or new schedule. 2. The system identifies every reservation still linked to that flight. 3. Each affected customer receives a notification that names the flight, the change, and the reservation identifier. 4. Notifications do not include full payment-card data or unnecessary personal details. 5. Customer reservation and flight-status views update to show the cancellation or modification. 6. A customer cannot cancel an entire flight; only authorized personnel can perform that action. | 9 | 3 | Cheyne Sersen
E-10 | Protected Records, Encryption, and Security Monitoring | As an airline stakeholder, I want reservation, payment, cancellation, and agent-sales records protected and auditable so that the web platform remains secure and trustworthy for customers and staff. | 1. All pages and APIs that handle accounts, reservations, payments, or agent data require HTTPS and an authenticated session. 2. Stored personal data and any retained payment references are encrypted at rest. 3. Role-based access is enforced on the server; hiding a menu item is not the only control. 4. Security events are logged, including failed sign-ins, payment failures, reservation access denials, and flight-cancellation actions. 5. User-supplied input is validated and encoded so that injection or script attacks cannot read or change another user's records. 6. A customer can view only that customer's records; an agent can view only the operational data allowed for that agent's role. | 10 | 3 | Preston Schave

## Sprint 1
Sprint #1Tracking Sheet
|  | Project |  | Online Airline Reservation and Flight Management System
|  | Sprint # |  | 1
|  | Start date |  | 2026-10-06
|  |  | Total Team Members | 4
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2026-10-06 | 2026-10-07 | 2026-10-08 | 2026-10-09 | 2026-10-10 | 2026-10-11 | 2026-10-12 | 2026-10-13 | 2026-10-14 | 2026-10-15 | 2026-10-16 | 2026-10-17 | 2026-10-18 | 2026-10-19
T1-01 | NF-01 | Create the GitHub repository, branching rules, and pull-request checklist so Sprint 1 work can be reviewed before merge. | Preston Schave | 1.5 | 2026-10-06: 0.5; 2026-10-07: 0.2; 2026-10-08: 0.2; 2026-10-09: 0.2; 2026-10-10: 0.25; 2026-10-11: 0.25
T1-02 | NF-01 | Stand up the local/test environment with HTTPS, a relational database, and an application skeleton. | Preston Schave | 2 | 2026-10-06: 0.2; 2026-10-07: 0.25; 2026-10-08: 0.2; 2026-10-09: 0.5; 2026-10-10: 0.5; 2026-10-11: 0.5
T1-03 | NF-01 | Design and script the data model for users, roles, flights, destinations, and reservations. | Preston Schave | 2 | 2026-10-06: 0.5; 2026-10-07: 0.5; 2026-10-08: 0.5; 2026-10-09: 0.25; 2026-10-10: 0.2; 2026-10-11: 0.2
T1-04 | NF-02 | Facilitate Sprint Planning: confirm the Sprint 1 goal, owners, estimates, and Definition of Done. | Sawyer Smith | 2 | 2026-10-06: 0.5; 2026-10-07: 0.5; 2026-10-08: 0.25; 2026-10-09: 0.25; 2026-10-10: 0.25; 2026-10-11: 0.25; 2026-10-13: 0.1; 2026-10-14: 0.1
T1-05 | E-01 | Create user/role tables and the registration API that requires a unique email and the project password rules. | Preston Schave | 2 | 2026-10-06: 0.5; 2026-10-07: 0.5; 2026-10-08: 0.5; 2026-10-09: 0.2; 2026-10-10: 0.2; 2026-10-11: 0.25
T1-06 | E-01 | Implement salted password hashing so the full password is never stored or displayed. | Preston Schave | 1 | 2026-10-06: 0.2; 2026-10-07: 0.2; 2026-10-08: 0.2; 2026-10-09: 0.2; 2026-10-10: 0.2; 2026-10-11: 0.2
T1-07 | E-01 | Build the customer registration screen and validation that matches the password rules. | Cheyne Sersen | 2 | 2026-10-06: 0.25; 2026-10-07: 0.25; 2026-10-08: 0.25; 2026-10-09: 0.25; 2026-10-10: 0.5; 2026-10-11: 0.5; 2026-10-13: 0.5; 2026-10-15: 0.2
T1-08 | E-01 | Implement the sign-in API with a generic error that does not confirm whether an email is registered. | Preston Schave | 1.5 | 2026-10-06: 0.25; 2026-10-07: 0.25; 2026-10-08: 0.25; 2026-10-09: 0.25; 2026-10-10: 0.25; 2026-10-11: 0.25
T1-09 | E-01 | Build customer and agent login screens that send each role only to the screens that role may use. | Cheyne Sersen | 2 | 0.25 | 0.25 | 0.5 | 0.5 | 0.25 | 0.25 |  | 0.2 | 0.2 | 0.2
T1-10 | E-01 | Implement logout and session timeout so protected pages and APIs reject an expired session. | Preston Schave | 1.5
T1-11 | E-01 | Enforce server-side authorization so another person's reservation, payment, or agent data cannot be viewed. | Preston Schave | 2
T1-12 | E-01 | Write and run tests for registration, failed login, timeout, and customer/agent role isolation. | Cheyne Sersen | 2 | 2026-10-06: 0.25; 2026-10-07: 0.25; 2026-10-08: 0.5; 2026-10-09: 0.5; 2026-10-10: 0.25; 2026-10-11: 0.25; 2026-10-13: 0.2; 2026-10-15: 0.5
T1-13 | E-02 | Seed sample flights and destinations; implement search by origin, destination, and travel date. | Preston Schave | 2 | 2026-10-12: 0.2; 2026-10-13: 0.2; 2026-10-14: 0.2; 2026-10-15: 0.5
T1-14 | E-02 | Return schedule and seat availability only; do not include another customer's name, reservation, or payment data. | Preston Schave | 1 | 2026-10-13: 0.2; 2026-10-15: 0.2
T1-15 | E-02 | Build the flight-search form and reject incomplete or invalid origin, destination, or date with a helpful message. | Cheyne Sersen | 2 | 2026-10-06: 0.5; 2026-10-07: 0.5; 2026-10-08: 0.25; 2026-10-09: 0.25; 2026-10-10: 0.25; 2026-10-11: 0.25
T1-16 | E-02 | Display matching flights with destination, times, and availability, or a clear no-results message. | Cheyne Sersen | 1.5 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 | 0.25 |  | 0.2 | 0.2 | 0.2
T1-17 | E-02 | Test search success, no-results, invalid input, and PII isolation on results. | Cheyne Sersen | 1.5 | 2026-10-15: 0.5
T1-18 | E-03 | Implement the reservation record, unique reservation identifier, and create-reservation API for signed-in customers. | Preston Schave | 2
T1-19 | E-03 | Reject a booking when the flight is no longer available and tell the customer to choose another flight. | Preston Schave | 1
T1-20 | E-03 | Build passenger-detail and confirm-reservation screens for an authenticated customer. | Cheyne Sersen | 2 | 2026-10-13: 0.2; 2026-10-15: 0.2
T1-21 | E-03 | Allow a signed-in customer to retrieve only their own reservation by identifier. | Preston Schave | 1.5
T1-22 | E-03 | Test reservation create, sold-out handling, retrieval, and protection against overwriting another booking. | Cheyne Sersen | 2 | 2026-10-15: 0.5
T1-23 | NF-01 | Add input validation and output encoding on Sprint 1 forms and APIs to reduce injection and script attacks. | Preston Schave | 2 | 2026-10-14: 0.5
T1-24 | NF-02 | Daily Scrum for Sprint 1 (time-boxed 15 minutes on each of 10 working days). | Sawyer Smith | 2.5 | 2026-10-06: 0.25; 2026-10-07: 0.25; 2026-10-08: 0.25; 2026-10-09: 0.25; 2026-10-10: 0.25; 2026-10-11: 0.25; 2026-10-13: 0.2; 2026-10-14: 0.2
T1-25 | NF-02 | Sprint Review / demo of registration, sign-in, search, and reservation to the Product Owner. | Kendal Runnels | 2 | 2026-10-06: 0.2; 2026-10-08: 0.2; 2026-10-11: 0.2
T1-26 | NF-02 | Sprint Retrospective and update of API, schema, and UI documentation for completed Sprint 1 work. | Sawyer Smith | 2 | 2026-10-13: 0.2; 2026-10-15: 0.2
T1-27 | NF-02 | Product Owner acceptance against Sprint 1 acceptance criteria and the Definition of Done. | Kendal Runnels | 1.5 | 2026-10-08: 0.2; 2026-10-10: 0.2; 2026-10-14: 0.5; 2026-10-15: 0.5; 2026-10-16: 0.3
T1-28 | NF-01 | Accessibility pass on registration, login, and search screens (labels, keyboard access, and readable errors). | Cheyne Sersen | 1.5 | 2026-10-13: 0.2
|  | Remaining units (actual) |  | 64 | 59.4 | 55.25 | 50.75 | 46.9 | 43.1 | 39.25 | 39.05 | 36.65 | 34.75 | 31.05 | 30.75 | 0 | 0 | 0
|  | Remaining units (ideal) |  |  | 46 | 41.4286 | 36.8571 | 32.2857 | 27.7143 | 23.1429 | 18.5714 | 14 | 9.4286 | 4.8571 | 0.28571 | -4.2857 | -8.8571 | -13.4286
[10 empty] | 0 | 49.5 | [5 empty] | 0 | 0.2
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Sprint 2
Sprint #2Tracking Sheet
|  | Project |  | Online Airline Reservation and Flight Management System
|  | Sprint # |  | 2
|  | Start date |  | 2026-10-20
|  |  | Total Team Members | 4
[5 empty] | week 1 | [6 empty] | week 2
[5 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14
Task ID | Story ID | Description | Responsibility | Initial estimate | 2026-10-20 | 2026-10-21 | 2026-10-22 | 2026-10-23 | 2026-10-24 | 2026-10-25 | 2026-10-26 | 2026-10-27 | 2026-10-28 | 2026-10-29 | 2026-10-30 | 2026-10-31 | 2026-11-01 | 2026-11-02
T2-01 | NF-01 | Prepare the payment-test environment and audit-log storage. Do not connect a live card processor in this sprint. | Preston Schave | 2 | 2026-10-20: 0.2; 2026-10-21: 0.2; 2026-10-22: 0.2; 2026-10-23: 0.2; 2026-10-24: 0.2; 2026-10-25: 0.2
T2-02 | NF-02 | Facilitate Sprint Planning for Sprint 2: goal, selected stories, owners, and estimates. | Sawyer Smith | 2 | 2026-10-20: 0.2; 2026-10-21: 0.2; 2026-10-22: 0.2; 2026-10-23: 0.2; 2026-10-24: 0.2; 2026-10-25: 0.2
T2-03 | E-04 | Accept payment only for an existing unpaid reservation owned by the signed-in customer. | Preston Schave | 1.5 | 2026-10-20: 0.2; 2026-10-21: 0.2; 2026-10-22: 0.2; 2026-10-23: 0.2; 2026-10-24: 0.2; 2026-10-25: 0.2
T2-04 | E-04 | Submit card data over HTTPS and do not store the full card number in the application database. | Preston Schave | 2 | 2026-10-20: 0.2; 2026-10-21: 0.2; 2026-10-22: 0.2; 2026-10-23: 0.2; 2026-10-24: 0.2; 2026-10-25: 0.2
T2-05 | E-04 | On a successful payment, create a ticket-sale record linked to the reservation, flight, and destination. | Preston Schave | 2 | bar: 2026-10-26
T2-06 | E-04 | On a declined or failed payment, do not issue a ticket and show a clear failure message. | Preston Schave | 1.5 | bar: 2026-10-26
T2-07 | E-04 | Write each payment attempt to an audit log using a masked card reference (last four digits only). | Preston Schave | 1.5 | bar: 2026-10-27
T2-08 | E-04 | Reject tampered or replayed payment requests so a prior charge cannot be resubmitted as a new sale. | Preston Schave | 1.5 | bar: 2026-10-27
T2-09 | E-04 | Build the payment form and the success and failure screens for the customer. | Cheyne Sersen | 2 | 2026-10-20: 0.25; 2026-10-21: 0.25; 2026-10-22: 0.25; 2026-10-23: 0.25; 2026-10-24: 0.25; 2026-10-25: 0.25
T2-10 | E-04 | Test payment success, decline, ownership, masking, and replay rejection. | Cheyne Sersen | 2 | bar: 2026-10-27 to 2026-10-28
T2-11 | E-05 | Build a signed-in reservation list that shows only the current customer's bookings. | Cheyne Sersen | 2 | 2026-10-20: 0.2; 2026-10-21: 0.2; 2026-10-22: 0.2; 2026-10-23: 0.2; 2026-10-24: 0.2; 2026-10-25: 0.2
T2-12 | E-05 | Show flight, destination, passenger information, ticket/payment status, and the reservation identifier. | Cheyne Sersen | 1.5 | 2026-10-27: 1; 2026-10-28: 0.5
T2-13 | E-05 | Return access-denied or not-found when another customer's reservation identifier is requested. | Preston Schave | 1.5 | 2026-10-20: 0.2; 2026-10-21: 0.25; 2026-10-22: 0.25; 2026-10-23: 0.2; 2026-10-24: 0.2; 2026-10-25: 0.2
T2-14 | E-05 | Label canceled and unpaid reservations so the customer can tell them apart from confirmed tickets. | Cheyne Sersen | 1 | bar: 2026-10-29
T2-15 | E-05 | Test reservation-review isolation and status labeling. | Cheyne Sersen | 1.5 | 2026-10-29: 0.5; 2026-10-30: 1
T2-16 | E-06 | Implement flight-status lookup by flight number or by a reservation the customer owns. | Preston Schave | 2 | bar: 2026-10-30
T2-17 | E-06 | Display on time, delayed, or canceled with destination and times; do not list other passengers. | Cheyne Sersen | 1.5 | 2026-10-20: 0.2; 2026-10-21: 0.2; 2026-10-22: 0.2; 2026-10-23: 0.2; 2026-10-24: 0.2; 2026-10-25: 0.2; 2026-11-02: 1
T2-18 | E-06 | Return a not-found message for an unknown flight number instead of an error page. | Cheyne Sersen | 1 | 2026-10-30: 0.5; 2026-10-31: 0.5
T2-19 | E-06 | Test status lookup, passenger privacy, and unknown-flight handling. | Cheyne Sersen | 1.5 | 2026-10-31: 1; 2026-11-01: 0.5
T2-20 | E-07 | Build authenticated agent views for flights, destinations, reservations, and ticket-sale records. | Preston Schave | 2.5 | 2026-10-30: 1; 2026-10-31: 1.5
T2-21 | E-07 | Allow an authorized agent to update flight time or status and reflect the change on later customer views. | Preston Schave | 2 | 2026-10-31: 0.5; 2026-11-01: 1.5
T2-22 | E-07 | Block customers from agent operations screens and APIs. | Preston Schave | 1.5 | 2026-11-01: 0.5; 2026-11-02: 1
T2-23 | E-07 | Record the agent, timestamp, and previous value for each operational change. | Preston Schave | 1.5 | bar: 2026-11-02
T2-24 | E-07 | Prevent deletion of audit history or payment logs. | Preston Schave | 1 | bar: 2026-11-02
T2-25 | E-07 | Test agent updates, customer denial of agent functions, and audit immutability. | Cheyne Sersen | 2 | bar: 2026-11-01 to 2026-11-02
T2-26 | NF-01 | Add validation and encoding on payment, reservation-review, status, and agent forms. | Preston Schave | 1.5 | 2026-11-02: 0.5
T2-27 | NF-02 | Daily Scrum for Sprint 2 (time-boxed 15 minutes on each of 10 working days). | Sawyer Smith | 2.5 | 2026-10-20: 0.2; 2026-10-21: 0.2; 2026-10-23: 0.2; 2026-10-28: 0.5; 2026-10-29: 0.5; 2026-10-30: 0.5
T2-28 | NF-02 | Sprint Review / demo of payment, reservation review, flight status, and agent operations. | Kendal Runnels | 2 | bar: 2026-10-22; 2026-11-02
T2-29 | NF-02 | Sprint Retrospective and documentation update for Sprint 2 APIs, schema, and UI. | Sawyer Smith | 2 | 2026-10-31: 0.5; 2026-11-01: 0.5
T2-30 | NF-02 | Product Owner acceptance against Sprint 2 acceptance criteria and the Definition of Done. | Kendal Runnels | 1.5 | 2026-10-23: 0.5; 2026-11-01: 0.5
|  | Remaining units (actual) |  | 64 | 62.15 | 60.25 | 57.55 | 55.2 | 53.55 | 51.9 | 49.9 | 45.9 | 43.9 | 41.9 | 37.9 | 33.9 | 29.4 | 22.9
|  | Remaining units (ideal) |  |  | 59.4286 | 54.8571 | 50.2857 | 45.7143 | 41.1429 | 36.5714 | 32 | 27.4286 | 22.8571 | 18.2857 | 13.7143 | 9.1429 | 4.5714 | 0
[10 empty] | 0 | 51.5 | [5 empty] | 0 | 2
[10 empty] | 10 | 0 | [5 empty] | 10 | 0

## Planning Notes
Unit 3 Sprint Planning Notes
Online Airline Reservation and Flight Management System
Original Planning notes: Prepared by Michael Storch for CS491 Unit 3. High-priority epics from last week's product backlog were decomposed into Sprint 1 and Sprint 2 tasks. Initial estimates are in hours. Daily remaining (actual) cells on the sprint sheets are intentionally blank; those hours will be entered during development in CS492.Revised and updated by Kendal Runnels Product Owner with the current Project Team.
1. Epic selection and sprint goals
Last week's backlog already ranked work by customer value and technical dependency. A traveler cannot pay for or review a trip until an account, a search result, and a reservation exist. For that reason Sprint 1 pulls E-01 Secure Customer and Agent Access, E-02 Flight Search and Availability, and E-03 Create Flight Reservation, plus the infrastructure and Scrum ceremonies needed to start development. Sprint 1 goal: An authenticated customer can search available flights and create a reservation on a secure foundation. Planned effort: 49.5 hours (team capacity on the tracking sheet is 8 × 2 × 4 = 64 hours). Sprint 2 then completes the purchase path and the first airline-operations slice: E-04 Secure Credit Card Payment and Ticket Sale, E-05 Review and Manage Reservations, E-06 Flight Status Lookup, and E-07 Airline Flight and Reservation Operations. Sprint 2 goal: A customer can pay for a reservation, review that booking, and check flight status, and an agent can update flight records with an audit trail. Planned effort: 51.5 hours against the same 64-hour capacity. E-08 Agent Sales Tracking, E-09 Flight Cancellation and Customer Notification, and E-10 Protected Records, Encryption, and Security Monitoring remain in the product backlog for a later sprint. Security controls that those epics require in the first release (HTTPS, hashing, authorization, masked payments, audit logs) are still started inside E-01, E-04, and E-07 so the early sprints are not built as an insecure shell.
2. Decomposed user stories used to create the tasks
Each epic was split into smaller user stories before it was broken into hour-sized tasks. Story IDs on the sprint sheets point back to the parent epic (E-01 through E-07) or to a non-functional bucket (NF-01 infrastructure, NF-02 Scrum ceremonies).
Story ID | Parent / Sprint | User story
US-01 | E-01 / Sprint 1 | As a new customer, I want to register with a unique email and a password that meets the project rules so that I can create an account the airline can authenticate later.
US-02 | E-01 / Sprint 1 | As a customer or airline agent, I want to sign in under the correct role so that I only see the screens and records that role is allowed to use.
US-03 | E-01 / Sprint 1 | As a signed-in user, I want logout and session timeout to end access so that a shared or abandoned browser cannot keep my reservation or payment data open.
US-04 | E-02 / Sprint 1 | As a customer, I want to search flights by origin, destination, and travel date so that I can compare options that match my trip.
US-05 | E-02 / Sprint 1 | As a customer, I want search results to show schedule and seat availability without other travelers' personal data so that I can choose a flight without exposing someone else's booking.
US-06 | E-03 / Sprint 1 | As an authenticated customer, I want to enter passenger details and receive a unique reservation identifier so that my booking is recorded against the selected flight.
US-07 | E-03 / Sprint 1 | As a customer, I want the system to refuse a booking when the flight is gone or when the reservation belongs to someone else so that I cannot take another person's seat or record.
US-08 | E-04 / Sprint 2 | As a customer, I want to pay for my own unpaid reservation with a credit card over HTTPS so that I can complete the ticket purchase without visiting an agent.
US-09 | E-04 / Sprint 2 | As an airline stakeholder, I want failed payments to issue no ticket and successful payments to write a masked audit entry so that sales records stay accurate and card data is not stored in full.
US-10 | E-05 / Sprint 2 | As a signed-in customer, I want to review only my reservations and their ticket status so that I can confirm flight details after purchase.
US-11 | E-06 / Sprint 2 | As a customer, I want to look up a flight's current status without seeing other passengers so that I know whether travel is on time, delayed, or canceled.
US-12 | E-07 / Sprint 2 | As airline personnel, I want to view and update flight and reservation records, with each change audited, so that schedules stay accurate and customers cannot use agent functions.
US-13 | NF-01 / Both | As the development team, we need a reviewed repository, HTTPS test environment, and a core data model so that later features are built on a stable, inspectable foundation.
US-14 | NF-02 / Both | As the Scrum Team, we need Sprint Planning, Daily Scrum, Review/demo, Retrospective, and Product Owner acceptance in each sprint so that the work stays aligned with the Definition of Done.
3. Legal and ethical principles considered while creating the user stories
The product handles passenger identity, travel records, and credit-card payments. The stories and tasks were written so that privacy, security, honesty, and accountability are acceptance criteria, not afterthoughts. The principles below were applied to the epics selected for Sprints 1 and 2.
Principle | How it shaped the stories and tasks
Privacy and data minimization | Customers may view only their own reservations. Search and flight-status views show schedule and availability, not other passengers' names or contact data. Payment screens and logs keep card data to a masked reference. This follows the ethical duty not to expose personal travel information and supports privacy expectations such as purpose limitation: collect and display only what the feature needs.
Payment-card protection | E-04 requires HTTPS, forbids storing the full card number, masks audit entries, and rejects replayed charges. Those rules follow the spirit of PCI DSS: the application is not treated as a place to keep primary account numbers. A failed payment must not create a ticket, which also avoids an unfair charge-for-no-service outcome.
Security as a duty of care | E-01 stores salted password hashes, uses generic sign-in errors so the system does not confirm whether an email is registered, and ends access on logout or timeout. Authorization is enforced on the server, not only by hiding a menu. Input validation and encoding are Sprint 1/2 tasks so injection or script attacks are not left until E-10. These choices treat traveler and airline data as something the team is obligated to protect.
Honesty and non-deception | Search must say when no flights match. Booking must fail clearly when a flight is no longer available. Payment decline messages must not imply a ticket was issued. Flight status must match the airline record (on time, delayed, or canceled) and an unknown flight number must return not-found rather than a crash or a fake result. The stories do not allow the interface to oversell seats or hide a failed purchase.
Least privilege and role separation | Customers and agents sign in under distinct roles. Customers cannot open agent operations. Agents cannot treat customer self-service sales as their own (that fuller rule lives in E-08, but Sprint 2 already blocks customer use of agent APIs). This is both an access-control design and an ethical limit on what staff may see or change.
Accountability and record integrity | Agent schedule changes record the actor, time, and previous value. Audit and payment logs cannot be deleted. A customer cannot create or overwrite another customer's reservation. These rules support non-repudiation for airline operations and protect travelers from silent alteration of their bookings.
Fairness and equal treatment | Search, booking, and payment rules are the same for every customer account. Availability is based on remaining seats, not on hidden preference. Accessibility work (labels, keyboard access, readable errors) is included so the booking path is not limited to users who can only use a mouse or who can guess an unlabeled field.
Informed, limited communication | E-09 (notifications for cancellations) is not in Sprint 1 or 2, but the later story already forbids putting full card data or extra personal detail in a notice. Sprint 2 status and reservation views follow the same idea: tell the traveler what changed about their trip, not everything the database knows about other people.
4. Non-functional work included in both sprints
NF-01 covers infrastructure: repository and review process, HTTPS-capable test environment, data model, input validation, accessibility, and (in Sprint 2) a payment test harness that does not use live card processing. NF-02 covers Scrum ceremonies: Sprint Planning, Daily Scrum, Sprint Review/demo, Retrospective, documentation, and Product Owner acceptance. Those items are listed as tasks with estimates because they consume team time and because the course template is also the plan that will be tracked when CS492 development starts. Actual completion hours on the day columns are not filled. Entering them before the product is built would invent progress the team has not earned.